## Docs
In case any cell is highlighted in Red, that means the data is not exported correctly for that cell as it has exceeded the excel limit of 32767 characters
Angola Transmission | [13 empty] | Kalpataru Projects International Limited
Search Export To Excel
Project: | Angola Transmission
Generated By: | Mr Tushar Jadhav, Kalpataru Projects International Limited
Generated On: | Wednesday, 28 October 2026 7:00:22 PM
Number of Results:269
Showing Result 1 to 269
File | Discipline | Document No | Revision | Title | Status | Planned Submission Date | Revision Date | Date Reviewed | Document Type | Milestone Date | Type | Date Modified | Created By | Sub Discipline | Related Items | Lock | Category | Confidential | Current | File Name | Hyperlink | Packages | Review Source | Transmittal In | Transmitted | Review Status | Version
pdf | Design | L2-489-ANG-KPIL-GEN-TRR-DWG-6144 | 00 | Tower spotting data | Approved | 2025-10-08 | 2025-10-08 | 2025-10-09 | Line Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Line Layout |  | No | For Approval | No | Yes | L2-489-ANG-KPIL-GEN-TRR-DWG-6144-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244666401&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 2
zip | Design | L2-489-ANG-KPIL-GEN-TRR-RAP-7008 | 01 | Tower test report for TT YAAT Standard height +3m Body Extn+2m Leg Extn tower type tested to 100% loading | Approved | 2026-04-29 | 2026-04-29 |  | Tower Test Data |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L2-489-ANG-KPIL-GEN-TRR-RAP-7008-01.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510246143200&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 3
pdf | Design | L2-489-ANG-KPIL-GEN-TRR-RAP-7009 | 00 | Tower test report for TT FA Standard height +3m Body Extn+2m Leg Extn tower type tested to 100% loading | Approved | 2026-06-10 | 2026-06-10 |  | Tower Test Data |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L2-489-ANG-KPIL-GEN-TRR-RAP-7009-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510246718926&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 3
pdf | Design | L3-490-ANG-KPIL-ATB-TRR-DWG-3602 | 03 | Anti climbing device drawing | Approved | 2025-03-20 | 2025-03-20 | 2025-04-02 | Accessories |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-ATB-TRR-DWG-3602-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915871&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
pdf | Design | L3-490-ANG-KPIL-BNA-TRR-PLN-3600 | 02 | B/N drawing & Grip chart | Approved | 2025-02-25 | 2025-02-20 | 2025-03-04 | Accessories |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-BNA-TRR-PLN-3600-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915869&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
pdf | Design | L3-490-ANG-KPIL-BNA-TRR-PLN-3600-CC | 02 | BN drawing & Grip chart | Approved |  | 2025-02-02 | 2025-03-04 | Accessories |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-BNA-TRR-PLN-3600-CC-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242234949&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3377 | 02 | YAS Foundation Design in hard rock ( Class 1) | Approved | 2025-10-05 | 2025-10-05 | 2025-10-22 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3377-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916000&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
zip | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3378 | 05 | YAS Foundation Design in soft weathered rock (class 2) | Approved | 2025-07-14 | 2025-07-14 | 2025-07-23 | Foundation Design | 2025-07-14 | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | Yes (deliverables) | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3378-05.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916001&projectid=1073775070&cversion=1&tab=0 |  | General |  | false | Pending | 22
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3379 | 05 | YAS Foundation Design in good soil condition ( Class 3A) | Approved | 2025-07-14 | 2025-07-14 | 2025-07-23 | Foundation Design | 2025-07-14 | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | Yes (deliverables) | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3379-05.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916002&projectid=1073775070&cversion=1&tab=0 |  | General |  | false | Pending | 22
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3380 | 05 | YAS Foundation Design in good soil condition ( Class 3B) | Approved |  | 2025-07-14 | 2025-07-23 | Foundation Design | 2025-07-14 | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | Yes (deliverables) | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3380-05.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916003&projectid=1073775070&cversion=1&tab=0 |  | General |  | false | Pending | 21
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3381 | 05 | YAS Foundation Design in poor soil condition no water ( class 4A) | Approved | 2025-07-14 | 2025-07-14 | 2025-07-23 | Foundation Design | 2025-07-14 | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | Yes (deliverables) | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3381-05.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916004&projectid=1073775070&cversion=1&tab=0 |  | General |  | false | Pending | 22
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3382 | 05 | YAS Foundation Design in poor soil condition no water ( class 4B) | Approved | 2025-07-14 | 2025-07-14 | 2025-07-23 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | Yes (deliverables) | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3382-05.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916005&projectid=1073775070&cversion=1&tab=0 |  | General |  | false | Pending | 23
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3383 | 05 | YAS Foundation Design in poor soil condition without water ( class 5A) | Approved | 2025-07-14 | 2025-07-14 | 2025-07-23 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | Yes (deliverables) | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3383-05.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916006&projectid=1073775070&cversion=1&tab=0 |  | General |  | false | Pending | 22
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3384 | 05 | YAS Foundation Design in poor soil condition with water ( class 5B) | Approved | 2025-07-14 | 2025-07-14 | 2025-07-23 | Foundation Design | 2025-07-14 | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | Yes (deliverables) | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3384-05.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916007&projectid=1073775070&cversion=1&tab=0 |  | General |  | false | Pending | 22
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3385 | 05 | YAS Foundation Design in very poor soil condition ( class 6) | Approved | 2025-07-14 | 2025-07-14 | 2025-07-23 | Foundation Design | 2025-07-14 | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | Yes (deliverables) | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3385-05.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916008&projectid=1073775070&cversion=1&tab=0 |  | General |  | false | Pending | 22
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3386 | 00 | YAL Foundation Design in hard rock ( Class 1) | Approved | 2025-10-05 | 2025-10-05 | 2025-10-22 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3386-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916009&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
zip | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3387 | 03 | YAL Foundation Design in soft weathered rock (class 2) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3387-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916010&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
zip | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3388 | 03 | YAL Foundation Design in good soil condition ( Class 3A) | Approved | 2026-04-01 | 2026-04-01 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3388-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916011&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
zip | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3389 | 03 | YAL Foundation Design in good soil condition ( Class 3B) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3389-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916012&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
zip | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3390 | 03 | YAL Foundation Design in poor soil condition no water ( class 4A) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3390-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916013&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
zip | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3391 | 03 | YAL Foundation Design in poor soil condition no water ( class 4B) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3391-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916014&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
zip | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3392 | 03 | YAL Foundation Design in poor soil condition without water ( class 5A) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3392-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916015&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
zip | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3393 | 03 | YAL Foundation Design in poor soil condition with water ( class 5B) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3393-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916016&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
zip | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3394 | 03 | YAL Foundation Design in very poor soil condition ( class 6) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3394-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916017&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3395 | 00 | YAO Foundation Design in hard rock ( Class 1) | Approved | 2025-10-05 | 2025-10-05 | 2025-10-22 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3395-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916018&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3396 | 03 | YAO Foundation Design for class 2 | Approved | 2026-06-10 | 2026-06-10 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3396-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916019&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 18
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3397 | 03 | YAO Foundation Design for class 3A | Approved | 2026-06-10 | 2026-06-10 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3397-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916020&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 18
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3398 | 03 | YAO Foundation Design for class 3B | Approved | 2026-06-10 | 2026-06-10 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3398-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916021&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 18
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3399 | 03 | YAO Foundation Design for class 4A | Approved | 2026-06-10 | 2026-06-10 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3399-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916022&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 18
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3400 | 03 | YAO Foundation Design for class 4B | Approved | 2026-06-10 | 2026-06-10 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3400-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916023&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 19
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3401 | 02 | YAO Foundation Design in poor soil condition without water ( class 5A) | Approved | 2025-09-25 | 2025-09-25 | 2025-09-30 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3401-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916024&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 17
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3402 | 02 | YAO Foundation Design in poor soil condition with water ( class 5B) | Approved | 2025-09-25 | 2025-09-25 | 2025-09-30 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3402-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916025&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 18
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3403 | 02 | YAO Foundation Design in very poor soil condition ( class 6) | Approved | 2025-09-25 | 2025-09-25 | 2025-09-30 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3403-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916026&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 17
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3404 | 00 | YAR Foundation Design in hard rock ( Class 1) | Approved | 2025-10-05 | 2025-10-05 | 2025-10-22 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3404-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916027&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3405 | 02 | YAR Foundation Design in soft weathered rock (class 2) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3405-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916028&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 17
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3406 | 02 | YAR Foundation Design in good soil condition ( Class 3A) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3406-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916029&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 17
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3407 | 02 | YAR Foundation Design in good soil condition ( Class 3B) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3407-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916030&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 17
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3408 | 02 | YAR Foundation Design in poor soil condition no water ( class 4A) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3408-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916031&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 17
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3409 | 03 | YAR Foundation Design in poor soil condition no water ( class 4B) | For Review | 2026-10-12 | 2026-10-12 | 2026-10-12 | Foundation Design |  | Document | 2026-10-12 18:02 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3409-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916032&projectid=1073775070&cversion=1&tab=0 |  |  |  | true |  | 17
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3410 | 02 | YAR Foundation Design in poor soil condition without water ( class 5A) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3410-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916033&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 17
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3411 | 02 | YAR Foundation Design in poor soil condition with water ( class 5B) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3411-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916034&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 17
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3412 | 02 | YAR Foundation Design in very poor soil condition ( class 6) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3412-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916035&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 17
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3413 | 00 | YAT Foundation Design in hard rock ( Class 1) | Approved | 2025-10-05 | 2025-10-05 | 2025-10-22 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3413-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916036&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3414 | 02 | YAT Foundation Design in soft weathered rock (class 2) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3414-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916037&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 18
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3415 | 02 | YAT Foundation Design in good soil condition ( Class 3A) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3415-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916038&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 18
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3416 | 02 | YAT Foundation Design in good soil condition ( Class 3B) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3416-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916039&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 18
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3417 | 02 | YAT Foundation Design in poor soil condition no water ( class 4A) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3417-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916040&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 18
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3418 | 02 | YAT Foundation Design in poor soil condition no water ( class 4B) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3418-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916041&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 18
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3419 | 02 | YAT Foundation Design in poor soil condition without water ( class 5A) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3419-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320158&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3420 | 02 | YAT Foundation Design in poor soil condition with water ( class 5B) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3420-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320159&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3421 | 02 | YAT Foundation Design in very poor soil condition ( class 6) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3421-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320160&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3422 | 00 | YAA Foundation Design in hard rock ( Class 1) | Approved | 2025-10-05 | 2025-10-05 | 2025-10-22 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3422-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244020290&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3423 | 02 | YAA Foundation Design in soft weathered rock (class 2) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3423-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244020294&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3424 | 02 | YAA Foundation Design in good soil condition ( Class 3A) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3424-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244020298&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3425 | 02 | YAA Foundation Design in good soil condition ( Class 3B) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3425-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244020299&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3426 | 02 | YAA Foundation Design in poor soil condition no water ( class 4A) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3426-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244020303&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3427 | 02 | YAA Foundation Design in poor soil condition no water ( class 4B) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3427-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244020304&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3428 | 02 | YAA Foundation Design in poor soil condition without water ( class 5A) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3428-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244020305&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3429 | 02 | YAA Foundation Design in poor soil condition with water ( class 5B) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3429-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244020306&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3430 | 02 | YAA Foundation Design in very poor soil condition ( class 6) | Approved | 2025-09-29 | 2025-09-29 | 2025-10-10 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3430-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244020313&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3431 | 00 | FA Foundation Design in hard rock ( Class 1) | Approved | 2025-10-05 | 2025-10-05 | 2025-10-22 | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3431-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320170&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 9
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3432 | 01 | FA Foundation Design in soft weathered rock (class 2) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3432-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320171&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3433 | 01 | FA Foundation Design in good soil condition ( Class 3A) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3433-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320172&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3434 | 01 | FA Foundation Design in good soil condition ( Class 3B) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3434-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320173&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3435 | 01 | FA Foundation Design in poor soil condition no water ( class 4A) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3435-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320174&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3436 | 01 | FA Foundation Design in poor soil condition no water ( class 4B) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3436-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320175&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3437 | 01 | FA Foundation Design in poor soil condition without water ( class 5A) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3437-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320176&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3438 | 01 | FA Foundation Design in poor soil condition with water ( class 5B) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3438-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320177&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-CIV-FDN-DWG-3439 | 01 | FA Foundation Design in very poor soil condition ( class 6) | Approved | 2026-03-25 | 2026-03-25 |  | Foundation Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Foundation |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-CIV-FDN-DWG-3439-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320178&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
N/A | Procurement | L3-490-ANG-KPIL-ECO-FIN-INV-6000 | 01 | Monthly Invoice | Approved | 2025-02-01 | 2025-06-26 |  | Reports |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Financial |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916059&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
N/A | Procurement | L3-490-ANG-KPIL-ENV-ENV-QSE-1005 | 00 | Environmental and Social Management Plan - C (ESMP-C) | Approved | 2025-02-01 | 2025-10-28 |  | Quality Plan |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Environmental |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915879&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Procurement | L3-490-ANG-KPIL-GEN-ACC-MOS-3364-CC | 03 | Method Statement for Bush Clearing and Access Road | Approved |  | 2025-03-05 | 2025-04-26 | Reports |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Access Road |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-ACC-MOS-3364-CC-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242235078&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 8
pdf | Procurement | L3-490-ANG-KPIL-GEN-ACS-RAP-2011 | 01 | OPGW Hardware Fittings GTP & Drawings | Approved |  | 2025-01-16 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Optical Wire Technical Data |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-ACS-RAP-2011-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915842&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 15
pdf | Procurement | L3-490-ANG-KPIL-GEN-ALL-LIS-1001-CC | 02 | Master Document List | Approved |  | 2025-01-29 | 2025-04-26 | Reports |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | All |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-ALL-LIS-1001-CC-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242706082&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Procurement | L3-490-ANG-KPIL-GEN-ALL-PLN-1013-CC | 01 | Store Layout Plan | Approved |  | 2025-03-05 | 2025-03-21 | Reports |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | All |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-ALL-PLN-1013-CC-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242471480&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Procurement | L3-490-ANG-KPIL-GEN-AWS-PLN-3109 | 00 | Aviation Items Inspection Test Plan | Approved |  | 2025-01-09 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Aviation System |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-AWS-PLN-3109-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915851&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Procurement | L3-490-ANG-KPIL-GEN-AWS-PLN-3109-CC | 00 | Aviation Items Inspection Test Plan | Approved |  | 2025-01-09 | 2025-01-14 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Aviation System |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-AWS-PLN-3109-CC-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242488595&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-GEN-AWS-RAP-2013 | 01 | Aviation Items GTP & Drawings | Approved |  | 2025-02-03 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Aviation System |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-AWS-RAP-2013-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915844&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
pdf | Procurement | L3-490-ANG-KPIL-GEN-AWS-RAP-2013-CC | 01 | Aviation Items GTP & Drawings | Approved |  | 2025-02-03 | 2025-02-07 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Aviation System |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-AWS-RAP-2013-CC-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242488812&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-GEN-CAM-PLN-1014-CC | 00 | Client Accommodation - Plan & Layout | Approved |  | 2025-01-29 | 2025-03-21 | Others |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Camping |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-CAM-PLN-1014-CC-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242471975&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-GEN-CHW-PLN-3106 | 02 | Conductor Accessories & HW Fittings Inspection Test Plan | Approved |  | 2025-02-12 |  | Conductors |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Conductor Hardware fittings |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-CHW-PLN-3106-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915849&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 18
pdf | Procurement | L3-490-ANG-KPIL-GEN-CHW-PLN-3106-CC | 02 | Conductor Accessories & HW Fittings Inspection Test Plan | Approved |  | 2025-02-12 | 2025-02-24 | Conductors |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Conductor Hardware fittings |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-CHW-PLN-3106-CC-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242456812&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-GEN-CND-PLN-3103 | 00 | Conductor Inspection and Test Plan | Approved |  | 2024-12-30 |  | Conductors |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Conductors |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-CND-PLN-3103-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915846&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Procurement | L3-490-ANG-KPIL-GEN-CND-PLN-3103-CC | 00 | Conductor Inspection and Test Plan | Approved |  | 2024-12-30 | 2025-01-07 | Conductors |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Conductors |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-CND-PLN-3103-CC-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242488984&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
N/A | Procurement | L3-490-ANG-KPIL-GEN-CND-RAP-5008 | 00 | Conductor FAT Report-4 | Approved | 2025-06-15 | 2025-09-10 |  | Conductors |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Conductors |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320182&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
N/A | Procurement | L3-490-ANG-KPIL-GEN-CND-RAP-5009 | 01 | Conductor FAT Report-5 | Approved | 2025-07-15 | 2025-10-31 |  | Conductors |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Conductors |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320183&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
N/A | Procurement | L3-490-ANG-KPIL-GEN-CND-RAP-5010 | 00 | Conductor FAT Report-6 | Approved | 2025-08-15 | 2026-03-28 |  | Conductors |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Conductors |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320184&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
zip | Design | L3-490-ANG-KPIL-GEN-FA-TRR-PLN-3358 | 04 | 'Basic Body for tower type 'FA'- (0°-5°)' | Approved | 2026-05-07 | 2026-05-07 |  | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-FA-TRR-PLN-3358-04.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244399483&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
pdf | Design | L3-490-ANG-KPIL-GEN-FA-TRR-PLN-3359 | 01 | "-6BE Plan for tower type 'FA (0°-5°)' | Approved | 2025-10-13 | 2025-10-13 | 2025-10-22 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-FA-TRR-PLN-3359-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244399519&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Design | L3-490-ANG-KPIL-GEN-FA-TRR-PLN-3363 | 03 | "+2 M LE for tower type "FA" (0°-5°)" | Approved | 2025-10-29 | 2025-10-29 | 2025-10-30 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-FA-TRR-PLN-3363-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244684804&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 8
pdf | Procurement | L3-490-ANG-KPIL-GEN-GEO-MOS-3365 | 05 | Method Statement of Geotechnical Studies | Approved |  | 2025-03-28 |  | Reports |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Geotechnical |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-GEO-MOS-3365-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915855&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 18
pdf | Procurement | L3-490-ANG-KPIL-GEN-GEO-MOS-3365-CC | 05 | Method Statement of Geotechnical Studies | Approved |  | 2025-03-05 | 2025-04-03 | Reports |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Geotechnical |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-GEO-MOS-3365-CC-05.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242471338&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 7
pdf | Procurement | L3-490-ANG-KPIL-GEN-GRD-PLN-3102 | 00 | Earthing Material-Inspection Test Plan | Approved |  | 2025-01-17 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Earthing Details |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-GRD-PLN-3102-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915845&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Procurement | L3-490-ANG-KPIL-GEN-GRD-PLN-3102-CC | 00 | Earthing Material-Inspection Test Plan | Approved |  | 2025-01-17 | 2025-01-22 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Earthing Details |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-GRD-PLN-3102-CC-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242489135&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Design | L3-490-ANG-KPIL-GEN-GRD-PLN-3530 | 05 | Tower Earthing Arrangement Design & Drawing | Approved | 2025-09-11 | 2025-09-11 | 2025-09-12 | Accessories |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Earthing Details |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-GRD-PLN-3530-05.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916046&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
N/A | Procurement | L3-490-ANG-KPIL-GEN-GRD-RAP-5052 | 00 | Earthing Material FAT Report-1 | Approved | 2025-04-15 | 2026-01-19 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Earthing Details |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320221&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-GEN-INS-PLN-3105 | 00 | Insulator Inspection Test Plan | Approved |  | 2024-12-30 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Insulators |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-INS-PLN-3105-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915848&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Procurement | L3-490-ANG-KPIL-GEN-INS-PLN-3105-CC | 00 | Insulator Inspection Test Plan | Approved |  | 2024-12-30 | 2025-01-07 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Insulators |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-INS-PLN-3105-CC-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242489647&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-GEN-INS-RAP-2012 | 01 | Insulator GTP & Drawings | Approved |  | 2025-02-04 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Insulators |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-INS-RAP-2012-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915843&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 9
pdf | Procurement | L3-490-ANG-KPIL-GEN-INS-RAP-2012-CC | 02 | Insulator GTP & Drawings | Approved |  | 2025-02-04 | 2025-03-28 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Insulators |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-INS-RAP-2012-CC-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242489906&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
N/A | Procurement | L3-490-ANG-KPIL-GEN-INS-RAP-5020 | 00 | Insulator FAT Report-1 | Approved | 2025-09-15 | 2025-09-10 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Insulators |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320194&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
N/A | Procurement | L3-490-ANG-KPIL-GEN-INS-RAP-5021 | 00 | Insulator FAT Report-2 | Approved | 2025-10-15 | 2026-01-27 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Insulators |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320195&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-GEN-OHW-PLN-3107 | 01 | OPGW Accessories & Hardware Fittings Inspection Test Plan | Approved |  | 2025-01-16 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | OPGW Hardware fitting |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-OHW-PLN-3107-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915850&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 15
pdf | Procurement | L3-490-ANG-KPIL-GEN-OHW-PLN-3107-CC | 01 | OPGW Accessories & Hardware Fittings Inspection Test Plan | Approved |  | 2025-01-16 | 2025-01-22 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | OPGW Hardware fitting |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-OHW-PLN-3107-CC-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242489945&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
N/A | Procurement | L3-490-ANG-KPIL-GEN-OHW-RAP-5030 | 00 | OPGW Hardware Fittings FAT Report-1 | Approved | 2025-09-15 | 2025-12-25 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | OPGW Hardware fitting |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320199&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
N/A | Procurement | L3-490-ANG-KPIL-GEN-OPG-CHR-2009 | 01 | OPGW cable drum Schedule | Approved | 2025-02-28 | 2025-08-27 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | OPGW |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915898&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Procurement | L3-490-ANG-KPIL-GEN-OPG-PLN-3104 | 00 | OPGW Inspection Test Plan | Approved |  | 2024-12-31 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | OPGW |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-OPG-PLN-3104-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915847&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Procurement | L3-490-ANG-KPIL-GEN-OPG-RAP-2007 | 00 | OPGW GTP & Drawings | Approved |  | 2024-12-31 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | OPGW |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-OPG-RAP-2007-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915840&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
N/A | Procurement | L3-490-ANG-KPIL-GEN-OPG-RAP-5054 | 00 | OPGW FAT Report-1 | Approved | 2025-09-15 | 2026-01-20 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | OPGW |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320223&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-GEN-TRR-BRD-3606 | 01 | Bird Guard/Diverters | Approved | 2025-09-11 | 2025-09-11 | 2025-09-29 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-BRD-3606-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241916048&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-DBR-2000 | 03 | Design Criteria | Approved | 2025-09-28 | 2025-09-28 | 2025-10-17 | Line Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-DBR-2000-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915837&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 21
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-DBR-2000-CC | 02 | Design Criteria | Approved |  | 2025-01-22 | 2025-02-03 | Line Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-DBR-2000-CC-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242490020&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-DWG-3603 | 02 | Tower Identification drawing (Danger Plate, Phase Plate, Identification Plate, Aerial plate, Number plate) | Approved | 2025-01-23 | 2025-03-01 | 2025-03-14 | Accessories |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-DWG-3603-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915872&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-DWG-3604 | 02 | Pack Washer | Approved | 2025-02-20 | 2025-02-20 | 2025-02-27 | Accessories |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-DWG-3604-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915873&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-DWG-3604-CC | 02 | Pack Washer | Approved |  | 2025-02-20 | 2025-02-27 | Accessories |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-DWG-3604-CC-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242466099&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-DWG-3608 | 02 | General arrangement of Accessories Drawing | Approved | 2025-03-20 | 2025-03-20 | 2025-03-27 | Accessories |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-DWG-3608-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242334973&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 7
pdf | Procurement | L3-490-ANG-KPIL-GEN-TRR-PLN-3001-CC | 01 | Quality Assurance Plan for Bolts & Nuts | Approved |  | 2025-02-20 | 2025-03-21 | Accessories |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3001-CC-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242470267&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Procurement | L3-490-ANG-KPIL-GEN-TRR-PLN-3101 | 02 | Quality Assurance Plan for Towers | Approved | 2025-02-01 | 2025-02-12 | 2025-06-19 | Quality Plan |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | Yes (deliverables) | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3101-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915909&projectid=1073775070&cversion=1&tab=0 |  | General |  | false | Pending | 17
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3300 | 03 | Stub drawing for raised chimney for tower type 'YAS (0°-2°)' | Approved | 2025-04-08 | 2025-04-08 | 2025-04-15 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3300-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915923&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 8
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3301 | 01 | Template for tower type 'YAS (0°-2°)' | Approved | 2025-04-23 | 2025-04-23 | 2025-05-05 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3301-01.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915924&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3302 | 04 | Basic body for tower type 'YAS (0°-2°)' | Approved | 2025-04-10 | 2025-04-10 | 2025-04-21 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | Yes (deliverables) | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3302-04.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915925&projectid=1073775070&cversion=1&tab=0 |  | General |  | false | Pending | 13
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3303 | 01 | '-6M BE (Body Extn) for tower type 'YAS (0°-2°)' | Approved | 2025-08-04 | 2025-08-04 | 2025-08-06 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3303-01.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915926&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3304 | 03 | '-3M BE (Body Extn) for tower type 'YAS (0°-2°)' | Approved | 2025-08-04 | 2025-08-04 | 2025-08-06 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3304-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915927&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3305 | 04 | '+0M BE (Body Extn) for tower type 'YAS (0°-2°)' | Approved | 2025-08-14 | 2025-08-14 | 2025-08-19 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3305-04.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915928&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 18
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3306 | 03 | '+ 3M BE for tower type 'YAS (0°-2°)' | Approved | 2025-08-04 | 2025-08-04 | 2025-08-06 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3306-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915929&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 15
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3307 | 03 | '+ 6M BE for tower type 'YAS (0°-2°)' | Approved | 2025-08-04 | 2025-08-05 | 2025-08-06 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3307-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915930&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 15
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3308 | 03 | '+ 9M BE for tower type 'YAS (0°-2°)' | Approved | 2025-08-04 | 2025-08-04 | 2025-08-06 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3308-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915931&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 17
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3309 | 04 | '+ 12M BE for tower type 'YAS (0°-2°)' | Approved | 2025-04-10 | 2025-04-10 | 2025-04-21 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | Yes (deliverables) | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3309-04.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915932&projectid=1073775070&cversion=1&tab=0 |  | General |  | false | Pending | 12
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3310 | 05 | '- 2 M LE TO +2 M LE for tower type 'YAS (0°-2°)' | Approved | 2025-08-04 | 2025-08-04 | 2025-08-06 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | Yes (deliverables) | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3310-05.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915933&projectid=1073775070&cversion=1&tab=0 |  | General |  | false | Pending | 18
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3311 | 02 | Stub for raised Chimney for tower type 'YAO (2°-15°)' | Approved | 2025-08-21 | 2025-08-21 | 2025-08-21 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3311-02.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915934&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3312 | 01 | Template for tower type 'YAO (2°-15°)' | Approved | 2025-08-08 | 2025-08-08 | 2025-08-13 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3312-01.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915935&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3313 | 02 | Basic Body for tower type 'YAO (2°-15°)' | Approved | 2025-07-09 | 2025-07-09 | 2025-07-17 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3313-02.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915936&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 17
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3314 | 02 | '- 6M BE (Body Extension) for tower type 'YAO (2°-15°)' | Approved | 2025-09-10 | 2025-09-10 | 2025-09-19 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3314_02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915937&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 14
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3315 | 02 | '- 3M BE (Body Extension) for tower type 'YAO (2°-15°)' | Approved | 2025-09-10 | 2025-09-10 | 2025-09-19 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3315_02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915938&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 14
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3316 | 02 | ± 0M BE (Body Extension) for tower type 'YAO (2°-15°)' | Approved | 2025-09-10 | 2025-09-10 | 2025-09-19 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3316_02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915939&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 14
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3317 | 02 | '+ 3M LE (Leg Extension) for tower type 'YAO (2°-15°)' | Approved | 2025-07-09 | 2025-07-09 | 2025-07-17 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3317-02.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915940&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 15
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3318 | 01 | '+1mLE, +0mLE, -1mLE, -2mLE (Leg Extension) for tower type 'YAO (2°-15°)' | Approved | 2025-08-18 | 2025-08-18 | 2025-09-05 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3318.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915942&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 19
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3319 | 03 | Template for tower type 'YAL (0°-2°)' | Approved | 2026-03-26 | 2026-03-26 |  | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3319-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915943&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3320 | 02 | 'Basic body for tower type 'YAL (0°-2°)' | Approved | 2025-09-11 | 2025-09-11 | 2025-09-18 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3320-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915944&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 14
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3321 | 01 | '- 6M BE for tower type 'YAL (0°-2°)' | Approved | 2025-10-17 | 2025-10-17 | 2025-10-24 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3321-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915945&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3322 | 01 | '- 3M BE for tower type 'YAL (0°-2°)' | Approved | 2025-10-17 | 2025-10-17 | 2025-10-24 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3322-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915946&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3323 | 01 | "±0M BE for tower type 'YAL (0°-2°)" | Approved | 2025-10-17 | 2025-10-17 | 2025-10-25 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3323-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915947&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3324 | 01 | '+ 3M BE for tower type 'YAL (0°-2°)' | Approved | 2025-10-17 | 2025-10-17 | 2025-10-25 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3324-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915948&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 12
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3325 | 02 | "+ 6M BE for tower type 'YAL (0°-2°)" | Approved | 2025-10-17 | 2025-10-17 | 2025-10-28 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3325-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915949&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3326 | 02 | "+ 9M BE for tower type 'YAL (0°-2°)" | Approved | 2025-10-27 | 2025-10-27 | 2025-10-28 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3326-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915951&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3327 | 01 | '+ 12M BE for tower type 'YAL (0°-2°)' | Approved | 2025-10-17 | 2025-10-17 | 2025-10-25 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3327-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915952&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3328 | 01 | '+ 15M BE for tower type 'YAL (0°-2°)' | Approved | 2025-10-17 | 2025-10-17 | 2025-10-25 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3328-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915953&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3329 | 01 | "+ 18M BE for tower type 'YAL (0°-2°)" | Approved | 2025-10-18 | 2025-10-18 | 2025-10-25 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3329-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915954&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3330 | 02 | '+ 21M BE for tower type 'YAL (0°-2°)' | Approved | 2025-09-11 | 2025-09-11 | 2025-09-17 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3330_02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915955&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 14
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3331 | 02 | '+2 M LE for tower type (W/C +3/6/9/12/15/18/21MB) 'YAL (0°-2°)' | Approved | 2025-09-11 | 2025-09-11 | 2025-09-17 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3331_02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915956&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3332 | 01 | Stub for raised Chimney for tower type 'YAR (15°-30°)' | Approved | 2025-08-04 | 2025-08-04 | 2025-08-22 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3332-01.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915957&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3333 | 00 | Template for tower type 'YAR (15°-30°)' | Approved | 2025-08-12 | 2025-08-12 | 2025-08-27 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3333-00.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915958&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 9
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3334 | 04 | Basic Body for tower type 'YAR (15°-30°)' | Approved | 2025-09-10 | 2026-01-08 | 2025-09-15 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3334-04.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915959&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 19
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3335 | 01 | '- 6M BE for tower type 'YAR (15°-30°)' | Approved | 2025-09-15 | 2025-09-15 | 2025-09-30 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3335-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915960&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3336 | 01 | '- 3M BE for tower type 'YAR (15°-30°)' | Approved | 2025-09-15 | 2025-09-15 | 2025-09-30 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3336-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915961&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3337 | 01 | ± 0M BE for tower type 'YAR (15°-30°)' | Approved | 2025-09-15 | 2025-09-15 | 2025-09-30 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3337-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915962&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3338 | 03 | '+ 3M BE for tower type 'YAR (15°-30°)' | Approved | 2025-09-10 | 2025-09-10 | 2025-09-15 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3338-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915963&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 17
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3339 | 02 | '+2mLE for tower type 'YAR (15°-30°)' | Approved | 2025-08-22 | 2025-08-22 | 2025-09-05 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3339-02.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915964&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 14
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3340 | 00 | Stub for rasied Chimney for tower type YAAT | Approved | 2025-08-12 | 2025-08-12 | 2025-08-29 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3340-00.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915965&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3341 | 01 | Template for tower type "YAAT" | Approved | 2025-11-03 | 2025-11-03 | 2025-11-18 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3341-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915966&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 14
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3342 | 02 | Basic Body for tower type 'YAAT' | Approved | 2025-10-15 | 2025-10-15 | 2025-10-23 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3342-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915967&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 14
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3343 | 01 | "- 6M BE for tower type 'YAAT" | Approved | 2025-10-18 | 2025-10-18 | 2025-10-24 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3343-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915968&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 12
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3344 | 02 | "- 3M BE for tower type 'YAAT" | Approved | 2025-10-18 | 2025-10-18 | 2025-10-28 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3344-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915969&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3345 | 01 | "± 0M BE for tower type 'YAAT" | Approved | 2025-10-18 | 2025-10-18 | 2025-10-24 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3345-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915970&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 12
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3346 | 02 | '+ 3M LE for tower type 'YAAT' | Approved | 2025-10-15 | 2025-10-15 | 2025-10-23 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3346-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915971&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 14
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3347 | 02 | '+2 M LE for tower type 'YAAT' | Approved | 2025-10-15 | 2025-10-15 | 2025-10-23 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3347-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915972&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 15
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3357 | 00 | Template for tower type 'FA (3°)' | Approved | 2025-11-11 | 2025-11-11 | 2025-11-19 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3357-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915982&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 9
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3358 | 06 | "Basic Body-for tower type 'FA (0°-5°)" | Approved | 2026-05-21 | 2026-05-21 |  | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3358-06.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244821726&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3360 | 01 | "- 3M BE for tower type 'FA (0°-5°)" | Approved | 2025-10-23 | 2025-10-23 | 2025-10-27 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3360-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915985&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3361 | 01 | "± 0M BE for tower type 'FA (0°-5°)" | Approved | 2025-10-23 | 2025-10-23 | 2025-10-27 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3361-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915986&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-3362 | 02 | '+3M BE for tower type 'FA (3°)' | Approved | 2025-10-13 | 2025-10-13 | 2025-10-28 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-3362-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244403376&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 9
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7000 | 03 | '-2 M LE for tower type 'YAS (0°-2°)' | Approved | 2025-07-31 | 2025-07-31 | 2025-08-06 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7000-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076124&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 3
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7001 | 03 | '-1 M LE for tower type 'YAS (0°-2°)' | Approved | 2025-07-31 | 2025-07-31 | 2025-08-06 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7001-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076125&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 3
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7002 | 03 | '+-0 M LE for tower type 'YAS (0°-2°)' | Approved | 2025-07-31 | 2025-07-31 | 2025-08-06 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7002-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076126&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 3
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7003 | 03 | '+1 M LE for tower type 'YAS (0°-2°)' | Approved | 2025-07-31 | 2025-07-31 | 2025-08-06 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7003-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076127&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 3
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7005 | 01 | '-2 M LE (Leg Extension) for tower type 'YAO (2°-15°)' | Approved | 2025-08-19 | 2025-08-19 | 2025-09-05 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7005-01.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076075&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7006 | 01 | '-1 M LE (Leg Extension) for tower type 'YAO (2°-15°)' | Approved | 2025-08-19 | 2025-08-19 | 2025-09-05 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7006-01.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076076&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7007 | 01 | 0 M LE (Leg Extension) for tower type 'YAO (2°-15°)' | Approved | 2025-08-19 | 2025-08-19 | 2025-09-05 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7007-01.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076077&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7008 | 01 | '+1 M LE (Leg Extension) for tower type 'YAO (2°-15°)' | Approved | 2025-08-19 | 2025-08-19 | 2025-09-05 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7008-01.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076078&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7009 | 02 | "-2 M LE for tower type-'FA (0°-5°)" | Approved | 2025-10-29 | 2025-10-29 | 2025-10-29 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7009-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076092&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 7
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7010 | 02 | "-1 M LE for tower type 'FA (0°-5°)" | Approved | 2025-10-29 | 2025-10-29 | 2025-10-29 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7010-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076093&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 7
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7011 | 02 | "+-0 M LE for tower type 'FA (0°-5°)" | Approved | 2025-10-29 | 2025-10-29 | 2025-10-29 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7011-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076094&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 7
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7012 | 02 | "+1 M LE for tower type 'FA (0°-5°)" | Approved | 2025-10-29 | 2025-10-29 | 2025-10-30 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7012-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076095&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 7
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7013 | 01 | '-2 M LE for tower type 'YAR (15°-30°)' | Approved | 2025-09-15 | 2025-09-15 | 2025-09-30 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7013-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076084&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7014 | 01 | '-1 M LE for tower type 'YAR (15°-30°)' | Approved | 2025-09-15 | 2025-09-15 | 2025-09-30 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7014-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076085&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7015 | 01 | '+-0 M LE for tower type 'YAR (15°-30°)' | Approved | 2025-09-15 | 2025-09-15 | 2025-09-30 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7015-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076086&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7016 | 01 | '+1 M LE for tower type 'YAR (15°-30°)' | Approved | 2025-09-15 | 2025-09-15 | 2025-09-30 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7016-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076087&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7017 | 03 | '-2 MLE connected to +3BE, +6BE, +9BE, +12BE for Tower type YAS (0°-2°) | Approved | 2025-07-31 | 2025-07-31 | 2025-08-06 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7017-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244852205&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 2
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7018 | 03 | '-1 MLE connected to +3BE, +6BE, +9BE, +12BE for Tower type YAS (0°-2°) | Approved | 2025-07-31 | 2025-07-31 | 2025-08-06 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7018-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244852206&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 2
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7019 | 03 | '+0 MLE connected to +3BE, +6BE, +9BE, +12BE for Tower type YAS (0°-2°) | Approved | 2025-07-31 | 2025-07-31 | 2025-08-08 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7019-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244852207&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 2
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7020 | 03 | '+1 MLE connected to +3BE, +6BE, +9BE, +12BE for Tower type YAS (0°-2°) | Approved | 2025-07-31 | 2025-07-31 | 2025-08-06 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7020-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244852208&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 2
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7021 | 01 | "+1 M LE for tower type 'YAL (0°-2°)" | Approved | 2025-10-17 | 2025-10-17 | 2025-10-25 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7021-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076082&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7022 | 01 | "+2 M LE for tower type (-6B,-3B,0B) 'YAL (0°-2°)" | Approved | 2025-10-17 | 2025-10-17 | 2025-10-25 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7022-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076083&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7023 | 01 | "-2 M LE for tower type 'YAAT (30°-90°)(60°-90°)/(0°-30°)DE'" | Approved | 2025-10-18 | 2025-10-18 | 2025-10-24 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7023-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076088&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7024 | 01 | "-1 M LE for tower type 'YAAT (30°-90°)(60°-90°)/(0°-30°)DE' | Approved | 2025-10-18 | 2025-10-18 | 2025-10-24 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7024-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076089&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7025 | 01 | "±0 M LE for tower type 'YAAT (30°-90°)(60°-90°)/(0°-30°)DE'" | Approved | 2025-10-18 | 2025-10-18 | 2025-10-24 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7025-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076090&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7026 | 01 | "+1 M LE for tower type 'YAAT (30°-90°)(60°-90°)/(0°-30°)DE" | Approved | 2025-10-18 | 2025-10-18 | 2025-10-24 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7026-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076091&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7027 | 02 | "-2 M LE for tower type 'YAL (0°-2°)" | Approved | 2025-10-17 | 2025-10-17 | 2025-10-28 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7027-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076121&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7028 | 02 | "-1 M LE for tower type 'YAL (0°-2°)" | Approved | 2025-10-17 | 2025-10-17 | 2025-10-28 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7028-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076122&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7029 | 02 | "±0 M LE for tower type 'YAL (0°-2°)" | Approved | 2025-10-17 | 2025-10-17 | 2025-10-28 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7029-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244076123&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
zip | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7030 | 01 | Stub drawing for tower type 'YAL (0°-2°)' | Approved | 2025-08-20 | 2025-08-20 | 2025-09-03 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7030_R1.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244156358&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7031 | 02 | "-2m LE for 'YAL (0°-2°)' Connecting With BB,-3mBE,±0mBE" | Approved | 2025-10-17 | 2025-10-17 | 2025-10-28 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7031-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244718121&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7032 | 01 | "- 1m LE for 'YAL (0°-2°)' Connecting With BB,-3mBE,±0mBE" | Approved | 2025-10-17 | 2025-10-17 | 2025-10-25 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7032-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244718169&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7033 | 02 | "±0m LE for 'YAL (0°-2°)' Connecting With BB,-3mBE,±0mBE" | Approved | 2025-10-17 | 2025-10-17 | 2025-10-28 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7033-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244718177&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-PLN-7034 | 01 | "+ 1m LE for 'YAL (0°-2°)' Connecting With BB,-3mBE,±0mBE)" | Approved | 2025-10-17 | 2025-10-17 | 2025-10-25 | Drawings |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-PLN-7034-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244718478&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-2001 | 00 | Sag tension calculations | Approved | 2024-12-31 | 2024-12-31 | 2025-01-09 | Line Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-2001-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915838&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 17
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-3201 | 04 | Design calculation for tower type 'YAS (0°-2°)' | Approved | 2025-08-06 | 2025-08-06 | 2025-08-13 | Tower Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-3201-04.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915852&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 22
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-3202 | 04 | Design calculation for tower type 'YAO (2°-15°)' | Approved | 2025-06-17 | 2025-06-17 | 2025-07-01 | Tower Design | 2025-06-17 | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | Yes (deliverables) | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-3202-04.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915911&projectid=1073775070&cversion=1&tab=0 |  | General |  | false | Pending | 17
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-3203 | 02 | Design calculation for tower type 'YAL (0°-2°)' | Approved | 2025-08-14 | 2025-08-14 | 2025-09-02 | Tower Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-3203-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915912&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
zip | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-3204 | 02 | Design calculation for tower type 'YAR(15°-30°)' | Approved | 2025-06-27 | 2025-06-27 | 2025-08-27 | Tower Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-3204-02.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915913&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-3205 | 03 | "Design calculation for tower type 'YAAT' | Approved | 2025-10-03 | 2025-10-03 | 2025-10-10 | Tower Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-3205-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915914&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 16
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-3207 | 02 | Design calculation for tower type 'FA(5°)' | Approved | 2025-10-13 | 2025-10-13 | 2025-10-23 | Tower Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-3207-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915916&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 15
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-3208 | 03 | Stub design calculation for tower type 'YAS (0°-2°)' | Approved | 2025-04-08 | 2025-04-08 | 2025-04-15 | Stub Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-3208-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915853&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 20
zip | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-3209 | 02 | Stub design calculation for tower type 'YAO (2°-15°)' | Approved | 2025-08-20 | 2025-08-20 | 2025-08-21 | Stub Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-3209-02.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915917&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 14
zip | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-3210 | 01 | Stub design calculation for tower type 'YAL (0°-2°)' | Approved | 2025-08-20 | 2025-08-20 | 2025-09-03 | Stub Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-3210-01.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915918&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
zip | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-3211 | 01 | Stub design calculation for tower type 'YAR (15°-30°)' | Approved | 2025-08-04 | 2025-08-04 | 2025-08-22 | Stub Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-3211-01.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915919&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-3212 | 01 | Stub design calculation for tower type 'YAAT' | Approved | 2025-08-08 | 2025-09-08 | 2025-09-18 | Stub Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-3212-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915920&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-3214 | 01 | Stub design calculation for tower type 'FA(3°)' | Approved | 2025-10-14 | 2025-10-14 | 2025-10-23 | Stub Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-3214-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915922&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 14
N/A | Procurement | L3-490-ANG-KPIL-GEN-TRR-RAP-5037 | 00 | Tower Material FAT Report-3 | Approved | 2025-08-15 | 2025-09-10 |  | Reports |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320206&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
N/A | Procurement | L3-490-ANG-KPIL-GEN-TRR-RAP-5038 | 00 | Tower Material FAT Report-4 | Approved | 2025-09-15 | 2025-12-29 |  | Reports |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242320207&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-7004 | 00 | YAS Tower Test Report | Approved | 2025-06-02 | 2025-06-02 | 2025-06-13 | Reports |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-7004-0.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510243523741&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 3
zip | Tower | L3-490-ANG-KPIL-GEN-TRR-RAP-7005 | 01 | Tower test report for TT YAL Standard height +21m Body Extn+2m Leg Extn tower type tested to 100% loading | Approved | 2026-01-13 | 2026-01-13 | 2026-01-13 | Reports | 2026-01-13 | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-7005-01.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510245353485&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Design | L3-490-ANG-KPIL-GEN-TRR-RAP-7006 | 00 | Tower test report for YAO Standard height +3m Body Extn+2m Leg Extn tower type tested to 100% loading | Approved | 2025-09-18 | 2025-09-18 | 2025-09-29 | Tower Test Data |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-7006-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510244452067&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Tower | L3-490-ANG-KPIL-GEN-TRR-RAP-7007 | 00 | Tower test report for TTYAR Standard height +3mBody Extn+2m Leg Extn tower type to 100% loading | Approved | 2026-01-02 | 2026-01-02 |  | Others | 2026-01-02 | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GEN-TRR-RAP-7007.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510245353487&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 3
pdf | Procurement | L3-490-ANG-KPIL-GTP-AWS-PLN-3607 | 00 | Aviation items Manufacturing Quality Plan | Approved |  | 2025-01-09 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Aviation System |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GTP-AWS-PLN-3607-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915874&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Procurement | L3-490-ANG-KPIL-GTP-AWS-PLN-3607-CC | 00 | Aviation items Manufacturing Quality Plan | Approved |  | 2025-01-09 | 2025-01-14 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Aviation System |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GTP-AWS-PLN-3607-CC-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242490618&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-GTP-CND-PLN-3450 | 00 | Conductor Manufacturing Quality Plan | Approved |  | 2024-12-30 |  | Conductors |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Conductors |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GTP-CND-PLN-3450-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915856&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Procurement | L3-490-ANG-KPIL-GTP-CND-PLN-3450-CC | 00 | Conductor Manufacturing Quality Plan | Approved |  | 2024-12-30 | 2025-01-07 | Conductors |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Conductors |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GTP-CND-PLN-3450-CC-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242490662&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-GTP-CND-RAP-2002 | 00 | Conductor GTP and Drawings | Approved |  | 2024-12-19 |  | Conductors |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Conductors |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GTP-CND-RAP-2002-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915839&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Procurement | L3-490-ANG-KPIL-GTP-CND-RAP-2002-CC | 00 | Conductor GTP and Drawings | Approved |  | 2024-12-19 | 2025-01-07 | Conductors |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Conductors |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GTP-CND-RAP-2002-CC-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242512859&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-GTP-GRD-PLN-3532 | 00 | Earthing material- MQP | Approved |  | 2025-01-17 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Earthing Details |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GTP-GRD-PLN-3532-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915867&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Procurement | L3-490-ANG-KPIL-GTP-GRD-PLN-3532-CC | 00 | Earthing material- MQP | Approved |  | 2025-01-17 | 2025-01-22 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Earthing Details |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GTP-GRD-PLN-3532-CC-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242513536&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-GTP-HWF-PLN-3490 | 01 | Hardware Fittings Manufacturing Quality Plan | Approved |  | 2025-01-17 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Hardware fitting |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GTP-HWF-PLN-3490-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915862&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 15
pdf | Procurement | L3-490-ANG-KPIL-GTP-HWF-PLN-3490-CC | 01 | Hardware Fittings Manufacturing Quality | Approved |  | 2025-01-17 | 2025-01-22 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Hardware fitting |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GTP-HWF-PLN-3490-CC_01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242515762&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-GTP-INS-PLN-3480 | 00 | Insulator Manufacturing Quality Plan | Approved |  | 2024-12-30 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Insulators |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GTP-INS-PLN-3480-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915860&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Procurement | L3-490-ANG-KPIL-GTP-INS-PLN-3480-CC | 00 | Insulator Manufacturing Quality Plan | Approved |  | 2024-12-30 | 2025-01-07 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Insulators |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GTP-INS-PLN-3480-CC-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242516003&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-GTP-OPG-PLN-3470 | 00 | OPGW Manufacturing Quality Plan | Approved |  | 2024-12-31 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | OPGW |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GTP-OPG-PLN-3470-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915858&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Procurement | L3-490-ANG-KPIL-GTP-OPG-PLN-3520 | 00 | OPGW accessories & Hardware Fittings Manufacturing Quality Plan | Approved |  | 2024-12-31 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | OPGW |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-GTP-OPG-PLN-3520-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915864&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Procurement | L3-490-ANG-KPIL-MGT-ALL-PLN-1003-CC | 01 | Master project schedule (detailed schedule) | Approved |  | 2025-01-13 | 2025-01-16 | Reports |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | All |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-MGT-ALL-PLN-1003-CC-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242516365&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
N/A | Procurement | L3-490-ANG-KPIL-QUA-TRR-RAP-3001 | 02 | Manufacturers Quality Plan for Towers, Bolts & Nuts | Approved | 2025-02-01 | 2025-06-05 |  | Quality Plan |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915899&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Design | L3-490-ANG-KPIL-QUA-TRR-RAP-3004 | 03 | YAS Standard height +12m Body Extn +2m Leg Extn tower type tested up to destruction | Approved | 2025-04-17 | 2025-04-17 | 2025-04-23 | Tower Test Data |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-QUA-TRR-RAP-3004-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915902&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
pdf | Design | L3-490-ANG-KPIL-QUA-TRR-RAP-3004-CC | 03 | YAS Standard height +12m Body Extn +2m Leg Extn tower type tested up to destruction | Approved |  | 2025-03-01 | 2025-04-23 | Tower Test Data |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-QUA-TRR-RAP-3004-CC-03.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242471500&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 7
pdf | Design | L3-490-ANG-KPIL-QUA-TRR-RAP-3005 | 00 | YAL Standard height +21m Body Extn+2m Leg Extn tower type tested to 100% loading | Approved | 2025-11-24 | 2025-11-24 | 2025-12-01 | Tower Test Data |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-QUA-TRR-RAP-3005-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915903&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
zip | Design | L3-490-ANG-KPIL-QUA-TRR-RAP-3006 | 02 | YAO Standard height +3m Body Extn+2m Leg Extn tower type tested to 100% loading | Approved | 2025-08-12 | 2025-08-12 | 2025-08-19 | Tower Test Data |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-QUA-TRR-RAP-3006-02.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915904&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 12
pdf | Design | L3-490-ANG-KPIL-QUA-TRR-RAP-3007 | 01 | YAR Standard height +3mBody Extn+2m Leg Extn tower type to 100% loading | Approved | 2025-11-06 | 2025-11-06 | 2025-11-18 | Tower Test Data |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-QUA-TRR-RAP-3007-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915905&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 10
N/A | Design | L3-490-ANG-KPIL-QUA-TRR-RAP-3008 | 00 | Tower test data TT YAAT Standard height +3mBody Extn+2m Leg Extn tower type to 100% loading | Approved | 2025-04-30 | -1 |  | Tower Test Data |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915906&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 7
zip | Design | L3-490-ANG-KPIL-QUA-TRR-RAP-3010 | 01 | FA Standard height +3 Body Extn+2m Leg Exten tower type to 100% loading | Approved | 2026-05-06 | 2026-05-06 |  | Tower Test Data |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-QUA-TRR-RAP-3010-01.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915908&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 9
pdf | Design | L3-490-ANG-KPIL-STP-TRR-DWG-3601 | 02 | Step Bolt drawing | Approved | 2025-02-20 | 2025-02-20 | 2025-03-04 | Accessories |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-STP-TRR-DWG-3601-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915870&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 13
pdf | Design | L3-490-ANG-KPIL-STP-TRR-DWG-3601-CC | 02 | Step Bolt drawing | Approved |  | 2025-02-20 | 2025-03-04 | Accessories |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Tower |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-STP-TRR-DWG-3601-CC-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242470104&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
zip | Design | L3-490-ANG-KPIL-TOP-ALL-PLN-3371 | 03 | Detailed Plans and Profiles | Approved | 2025-08-09 | -1 | 2025-08-19 | Line Design |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | All |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TOP-ALL-PLN-3371-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915994&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 7
zip | Design | L3-490-ANG-KPIL-TOP-ENV-GEO-7035 | 03 | HYDROLOGICAL STUDIES REPORT PART-I | Approved | 2026-07-17 | 2026-07-17 |  | Reports |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Environmental |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TOP-ENV-GEO-7035-03.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510246143199&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
zip | Design | L3-490-ANG-KPIL-TOP-ENV-GEO-7036 | 00 | HYDROLOGICAL STUDIES REPORT PART-II | Approved | 2026-07-30 | 2026-07-30 |  | Reports |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Environmental |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TOP-ENV-GEO-7036-00.zip | https://asia2.aconex.com/ViewDoc?trackingid=1085367510247184227&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 2
pdf | Design | L3-490-ANG-KPIL-TOP-ENV-GEO-7037 | 00 | HYDROLOGICAL STUDIES REPORT PART-III | Approved | 2026-06-10 | 2026-06-10 |  | Reports |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Environmental |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TOP-ENV-GEO-7037-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510246726639&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Procurement | L3-490-ANG-KPIL-TTP-OPG-PLN-3500 | 00 | OPGW Accessories Type test plan & procedure | Approved |  | 2025-02-12 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | OPGW |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTP-OPG-PLN-3500-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242334914&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Procurement | L3-490-ANG-KPIL-TTP-OPG-PLN-3500-CC | 00 | OPGW Accessories Type test plan & procedure | Approved |  | 2025-02-12 | 2025-02-24 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | OPGW |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTP-OPG-PLN-3500-CC-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242456929&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-TTR-AWS-PLN-3609 | 00 | Aviation Items Type test report | Approved |  | 2025-01-09 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Aviation System |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTR-AWS-PLN-3609-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915875&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6
pdf | Procurement | L3-490-ANG-KPIL-TTR-AWS-PLN-3609-CC | 00 | Aviation Items Type test report | Approved |  | 2025-01-09 | 2025-01-14 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Aviation System |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTR-AWS-PLN-3609-CC-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242518839&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-TTR-CND-RAP-3451 | 00 | Conductor Type Test Report | Approved |  | 2024-12-30 |  | Conductors |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Conductors |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTR-CND-RAP-3451-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915857&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Procurement | L3-490-ANG-KPIL-TTR-CND-RAP-3451-CC | 00 | Conductor Type Test Report | Approved |  | 2024-12-30 | 2025-01-07 | Conductors |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Conductors |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTR-CND-RAP-3451-CC-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242518880&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-TTR-GRD-PLN-3533 | 01 | Earthing Material -Type Test Report | Approved |  | 2025-02-03 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Earthing Details |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTR-GRD-PLN-3533-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915868&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 11
pdf | Procurement | L3-490-ANG-KPIL-TTR-GRD-PLN-3533-CC | 01 | Earthing Material -Type Test Report | Approved |  | 2025-02-03 | 2025-02-07 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Earthing Details |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTR-GRD-PLN-3533-CC-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242519309&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-TTR-HWF-RAP-3491 | 02 | Hardware Fittings Type Test Report | Approved |  | 2025-02-12 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Hardware fitting |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTR-HWF-RAP-3491-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915863&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 18
pdf | Procurement | L3-490-ANG-KPIL-TTR-HWF-RAP-3491-CC | 02 | Hardware Fittings Type Test Report | Approved |  | 2025-02-12 | 2025-02-24 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Hardware fitting |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTR-HWF-RAP-3491-CC-02.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242456833&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-TTR-INS-RAP-3481 | 01 | Insulator Type Test Report | Approved |  | 2025-02-04 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Insulators |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTR-INS-RAP-3481-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915861&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 9
pdf | Procurement | L3-490-ANG-KPIL-TTR-INS-RAP-3481-CC | 01 | Insulator Type Test Report | Approved |  | 2025-02-04 | 2025-02-07 | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | Insulators |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTR-INS-RAP-3481-CC-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242519451&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
pdf | Procurement | L3-490-ANG-KPIL-TTR-OPG-RAP-3471 | 01 | OPGW Type Test Report | Approved |  | 2025-01-16 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | OPGW |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTR-OPG-RAP-3471-01.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915859&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 15
pdf | Procurement | L3-490-ANG-KPIL-TTR-OPG-RAP-3501 | 00 | FOC Type test report | Approved |  | 2025-01-27 |  | Bought-out Items |  | Document | 2026-09-07 22:05 | Kalpataru Projects International Limited | OPGW |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTR-OPG-RAP-3501-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242334977&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 4
pdf | Procurement | L3-490-ANG-KPIL-TTR-OPG-RAP-3501-CC | 00 | FOC Type test report | Approved |  | 2025-01-27 | 2025-02-05 | Bought-out Items |  | Document | 2026-09-07 22:06 | Kalpataru Projects International Limited | OPGW |  | No | For Approval | No | Yes | L3-490-ANG-KPIL-TTR-OPG-RAP-3501-CC-00.pdf | https://asia2.aconex.com/ViewDoc?trackingid=1085367510242519478&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 5
N/A | Procurement | L3-490-ANG-KPIL-VDP-CND-CHR-2004 | 04 | Vibration Damper placement Chart for CONDUCTOR | Approved | 2025-02-15 | 2025-12-24 |  | Conductors |  | Document | 2026-09-07 22:06 | Kalpataru Projects International Limited | Conductors |  | No | For Approval | No | Yes |  | https://asia2.aconex.com/ViewDoc?trackingid=1085367510241915894&projectid=1073775070&cversion=1&tab=0 |  |  |  | false |  | 6